## Sheet1
Milestone | Owner | Cost Days | Progress | Remaining days | Area | Feature | Description | Notes
M1 | Arthur VDH | 1 | 1 | 0 | Graphics | Car | Choose the model of car we would like to use for our game and create a design for it
M1 | Ryan Tiotuico | 1 | 1 | 0 | Gameplay | Car | Code for a working car that the user will play the game with
M1 | Ryan Tiotuico | 1 | 1 | 0 | Gameplay | Camera | Create the camera the user will use to see the game
M2 | Everyone | 7 | 7 | 0 | Gameplay | Environment | Create a road system that the car will follow on
M2 | Everyone | 7 | 7 | 0 | Gameplay | Environment | Create initial environments for the tracks to be made on
M2 | Arthur VDH | 5 | 5 | 0 | Gameplay | Checkpoints | Create checkpoints for the user to respawn at if they fall off the coure
M2 | Ryan Tiotuico | 5 | 5 | 0 | Gameplay | AI Opponent | Code for an AI cars to compete against the user
M2 | Ryan Tiotuico | 4 | 4 | 0 | Gameplay | Timer | Code for a timer to add to the screen to challenge the user
M3 | Ryan Tiotuico | 3 | 1.5 | 1.5 | Gameplay | Powerups | Code for a boost powerup that will grant the user faster speeds
M3 | Ryan Tiotuico | 1 | 0 | 1 | Graphics | Powerups | Design and create how the powerups will look
M3 | Arthur VDH | 6 | 3 | 3 | Graphics | Pause Menu | Create a pause menu that the user will be able to either reset the level, change the color of the car, or change the model of the car
M3 | Everyone | 3 | 1.5 | 1.5 | Graphics | Environment | Create the final design for the levels we are each developing
M3 | Arthur VDH | 3 | 0 | 3 | Gameplay | Title Page | Create a starting page that prompts the user with with mode/map they would like to play with
M4 | Everyone | 5 | 0 | 5 | Gameplay | Multiplayer | Add multiplayer as a feature to the game
M4 | Everyone | 5 | 1 | 5 | Gameplay | Multiplayer | Learn how to add a network to the game
[5 empty] | Deadline | Remaining (workdays) | Critical Path Buffer (workdays) | My Buffer (workdays)
| M1 Total | 3 | 100% | 0 | 2022-09-23 | 0 | 0
| M2 Total | 28 | 100% | 0 | 2022-10-21 | 0 | 0
| M3 Total | 20 | 30% | 14 | 2022-11-25 | 16.5 | 6 (Arthur VDH)
| M4 Total | 10 | 0% | 10 | 2022-12-16 | 38 | 0