## Sheet1
Milestone | Owner | Cost (days) | Progress | Remaining (days) | Area | Feature | Description
M1 | Arthur VDH | 6 | 100% | 0 | Graphics | Car Customization | Created code that allowed players to pick a color and decal for their car.
M1 | Adi S | 2 | 100% | 0 | Gameplay | Car Movement | Create code to allow the user to move the car.
M1 | Adi, Ryan, Arthur | 2 | 100% | 0 | Graphics | Landscapes | Create Initial landscapes for users to navigate and play.
M1 | Adi, Ryan, Arthur | 4 | 100% | 0 | Gameplay | Road System | Create the track in which users will drive on
M2 | Ryan T | 10 | 100% | 0 | Gameplay | AI Opponents | Code for a path that follows each track that allows users to race a computer opponent.
M2 | Ryan T | 2 | 100% | 0 | Gameplay | Timer | Created a timer code that would keep track of the current lap time, the total time, and the best lap time.
M2 | Adi, Ryan, Arthur | 10 | 100% | 0 | Graphics | Landscapes | Create update landscapes to use for relase of the game.
M2 | Arthur VDH | 3 | 100% | 0 | Menu | Esc Menu UI | Code for an in game menu that allows the user to either reset the level, go back to the main menu, or change the visuals on the car.
M2 | Ryan, Arthur | 6 | 100% | 0 | Gameplay | Game Control Class | Create code that controls how the game will run. This code will allow respawns, and find which checkpoint to send you back to.
M3 | Adi S | 4 | 100% | 0 | Menu | Menu UI | Code for a main menu that allows users to navigate to the different levels.
M3 | Ryan T | 6 | 100% | 0 | Gameplay | PowerUp | Create a power that will grant the user an advantage over the AI opponents.
M4 | Ryan and Arthur | 3 | 100% | 0 | Menu | Winner Indication Screen | Create a display for the user that checks if the AI beat them by displaying a "You Win or "Game Over" Screen
M4 | Adi, Ryan, Arthur | 5 | 100% | 0 | Bugs | Each Map | Go through our respective maps and fine tune and fix issues that the levels may have.
M4 | Adi | 10 | 100% | 0 | Gameplay | Each Map | Combine all the scenes and have it work with the main menu in one package
[5 empty] | Deadline | Remaining (workdays) | Critical Path Buffer (workdays) | My Buffer (workdays)
M1 Total |  | 14 | 100% | 0 | 2022-10-07 | 0 | 0 | 0
M2 Total |  | 31 | 100% | 0 | 2022-11-28 | 0 | 0 | 0
M3 Total |  | 10 | 100% | 0 | 2022-12-16 | 0 | 0 | 0
M4 Total |  | 18 | 100% | 0 | 2023-01-25 | 0 | 0 | 0
|  | Total dev days: | 55 | 100% | 0